## Dashboard
Green Belt Tollgate Checklist
Details entered in top section will appear automatically on all Tollgate Checklist pages:
Green Belt: | Enter Green Belt | Project Start Date: | Enter Date
Project Name: | Enter Project Name | Planned Completion Date: | Enter Date
Champion: | Enter Champion/Sponsor
Done (Y/N) | Phase
N | Introduction
N | Define
N | Measure
N | Analyze
N | Improve
N | Control
Once all items above are marked "Y", item below will automatically marked "Y".
N | All Tollgates Complete

## Green Belt Intro Tollgate
Green Belt Introduction Tollgate Checklist
Green Belt: | Enter Green Belt | Project Start Date: | Enter Date
Project Name: | Enter Project Name | Planned Completion Date: | Enter Date
Champion: | Enter Champion/Sponsor
Done (Y/N) | Introduction |  |  | Typical Duration (Hours)
N | Conduct an 8 Wastes Assessment |  |  | 1
N | Find at least one process improvement opportunity |  |  | 2
N | Enlist a Project Champion/Sponsor who will support you and the project |  |  | 1
N | Familiarize yourself with the DMAIC Roadmap |  |  | 1
Once all items above are marked "Y", item below will automatically marked "Y" and Dashboard will be updated. |  |  |  | 5
N | Define Tollgate Complete
Introduction Deliverables
Required |  | Supporting
N | 8 Wastes Checksheet | Project Selection Guide/Project Selection Tool
N | Approved Process Improvement Project | Draft Project Charter
N | Project Champion/Sponsor | Team Meeting Agenda
Project Storyboard
Tollgate Checklist

## Green Belt Define Tollgate
Green Belt Define Tollgate Checklist
Green Belt: | Enter Green Belt | Project Start Date: | Enter Date
Project Name: | Enter Project Name | Planned Completion Date: | Enter Date
Champion: | Enter Champion/Sponsor
Done (Y/N) | Define |  |  | Typical Duration (Hours)
N | Complete the elements of the Project Charter |  |  | 2
N | Collect the Voice of the Customer and make customer requirements measurable |  |  | 3
N | Conduct a Process (Gemba) Walk of the process being addressed |  |  | 8
N | Create a high level and detailed map of the current state |  |  | 3
N | Update Charter and inform Stakeholders |  |  | 2
Once all items above are marked "Y", item below will automatically marked "Y" and Dashboard will be updated. |  |  |  | 18
N | Define Tollgate Complete
Define Deliverables
Required |  | Supporting
N | Project Charter | A3
N | Voice of the Customer Translation Matrix | Project Selection Guide/Project Selection Tool
N | SIPOC | RACI Matrix or Action Plan
N | Process (Gemba) Walk | Process Walk Planning Checklist
N | Detailed Process Map (Swimlane or flow) | Process Walk Interview Sheet
N | Stakeholder Analysis | Spaghetti Map and/or Value Stream Map
N | Communication Plan | Project Storyboard

## Green Belt Measure Tollgate
Green Belt Measure Tollgate Checklist
Green Belt: | Enter Green Belt | Project Start Date: | Enter Date
Project Name: | Enter Project Name | Planned Completion Date: | Enter Date
Champion: | Enter Champion/Sponsor
Done (Y/N) | Measure |  |  | Typical Duration (Hours)
N | Select baseline measurements |  |  | 2
N | Develop a Data Collection Plan with Operational Definitions and create Check Sheets as needed |  |  | 4
N | Collect the Baseline Data |  |  | 4
N | Update Charter and inform Stakeholders |  |  | 2
Once all items above are marked "Y", item below will automatically marked "Y" and Dashboard will be updated. |  |  |  | 12
N | Measure Tollgate Complete
Measure Deliverables
Required |  | Supporting
N | Operational Definitions | Check Sheets
N | Data Collection Plan | Efficiency & Effectiveness Matrix
N | Process Baseline of Project Y | Spaghetti Map
Cost of Poor Quality Calculator
Process Walk Interview Sheet
Updated Charter, A3, Stakeholder Analysis and Communication Plan

## Green Belt Analyze Tollgate
Green Belt Analyze Tollgate Checklist
Green Belt: | Enter Green Belt | Project Start Date: | Enter Date
Project Name: | Enter Project Name | Planned Completion Date: | Enter Date
Champion: | Enter Champion/Sponsor
Done (Y/N) | Analyze |  |  | Typical Duration (Hours)
N | Identify potential root causes using Process Analsys, Data Analysis, Fishbone Diagrams, 5 Whys, etc. |  |  | 4
N | Develop root cause hypotheses |  |  | 4
N | Collect data, assess facts and observe the process to prove or disprove root cause hypotheses |  |  | 6
N | Update your Charter and inform Stakeholders |  |  | 2
Once all items above are marked "Y", item below will automatically marked "Y" and Dashboard will be updated. |  |  |  | 16
N | Analyze Tollgate Complete
Analyze Deliverables
Required |  | Supporting
N | Fishbone Diagram | Value Stream Map
N | 5 Whys | Detailed Map (Swimlane or Flow map)
N | Root Cause Hypothesis Confirmation Worksheet | Value-Added Flow Analysis of cycle time projects
Data Collection Plan
Check Sheets
Pareto Charts, Histograms, Run Charts, Box Plots, Scatter Plots, etc.
Updated Charter, A3, Stakeholder Analysis and Communication Plan

## Green Belt Improve Tollgate
Green Belt Improve Tollgate Checklist
Green Belt: | Enter Green Belt | Project Start Date: | Enter Date
Project Name: | Enter Project Name | Planned Completion Date: | Enter Date
Champion: | Enter Champion/Sponsor
Done (Y/N) | Improve |  |  | Typical Duration (Hours)
N | Use team brainstorming to generate solutions that address the root causes |  |  | 3
N | Select and develop solutions |  |  | 4
N | Pilot solutions if needed and plan for implementation |  |  | 4
N | Implement solutions to address root causes |  |  | 3
N | Verify that solutions improved the process "Y" |  |  | 2
Once all items above are marked "Y", item below will automatically marked "Y" and Dashboard will be updated. |  |  |  | 16
N | Improve Tollgate Complete
Improve Deliverables
Required |  | Supporting
N | Solution Selection Matrix showing solutions | Improved "To Be" Map
N | Implementation Plan | 5S Assessment
N | Run Chart verifying improvement of Project Y | Weighted Criteria Matrix comparing solutions
Cross-Training Matrix
Visual Management Checklist
FMEA showing risk mitigation of changes
Pilot Checklist
Updated Charter/A3, Stakeholder Analysis and Communication Plan

## Green Belt Control Tollgate
Green Belt Control Tollgate Checklist
Green Belt: | Enter Green Belt | Project Start Date: | Enter Date
Project Name: | Enter Project Name | Planned Completion Date: | Enter Date
Champion: | Enter Champion/Sponsor
Done (Y/N) | Control |  |  | Typical Duration (Hours)
N | Create a system and/or process to monitor the results |  |  | 4
N | Complete documentation of the processes and procedures |  |  | 4
N | Create Response Plans in case there is a drop in performance |  |  | 2
N | Hand over formal ownership to the Process Owner |  |  | 2
N | Determine the next process improvement focus |  |  | 1
Once all items above are marked "Y", item below will automatically marked "Y" and Dashboard will be updated. |  |  |  | 13
N | Control Tollgate Complete
Control Deliverables
Required |  | Supporting
N | Monitoring & Response Plan | A3
N | Control Chart of Project "Y" | Monitoring Plan Map
N | Executive Summary | New Procedure Audit
N | Project Storyboard | Innovation Transfer Opportunities
Project Closure
8 Wastes Assessment

## Estimated Meeting Times
Estimated Meeting Times
Define | Typical Duration (Hours)
Complete the elements of the Project Charter | 2
Collect the Voice of the Customer and make customer requirements measurable | 3
Conduct a Process (Gemba) Walk of the process being addressed | 8
Create a high level and detailed map of the current state | 3
Update Charter and inform Stakeholders | 2
Estimated Meeting Hours for "Define" | 18
Measure
Select baseline measures | 2
Develop a Data Collection Plan with Operational Definitions and create Check Sheets as needed | 4
Collect the baseline data | 4
Update Charter and Inform stakeholders | 2
Estimated Meeting Hours for "Measure" | 12
Analyze
Identify potential root causes using Process Analsys, Data Analysis, Fishbone Diagrams, 5 Whys, etc. | 4
Develop root cause hypothesis | 4
Collect data, assess facts and observe the process to prove or disprove root cause hypotheses | 6
Update your Charter and inform Stakeholders | 2
Estimated Meeting Hours for "Analyze" | 16
Improve
Use team brainstorming to generate solutions | 3
Select and develop solutions | 4
Pilot solutions if needed and plan for implementation | 4
Implement solutions to address root causes | 3
Verify that solutions improved the process "Y" | 2
Estimated Meeting Hours for "Improve" | 16
Control
Create a system and/or process to monitor the results | 4
Complete documentation of processes & procedures | 4
Create Response Plans in case there is a drop in performance performance performance | 2
Hand over formal ownership to the Process Owner | 1
Estimated Meeting Hours for "Control" | 13

## (Original) Est. Meeting Times (hidden)
Define | Typical Duration (Hours)
Complete the elements of the Project Charter | 2
Collect the Voice of the Customer and make customer requirements measurable | 3
Create a high level and detailed map of the current state | 3
Create Stakeholder Communication Plan | 2
Update charter and project documentation | #REF!
Estimated Meeting Hours for "Define" | 18
Measure
Select baseline measures | 2
Develop a data collection plan with Operational Definitions and create data sheets if needed | 4
Collect the baseline data | 4
Update charter and inform stakeholders | 2
Estimated Meeting Hours for "Measure" | 12
Analyze
Identify potential causes (Process Maps, 5 Why’s, Fishbone) | 4
Develop root cause hypothesis | 4
Collect facts or data to support root cause hypothesis | 6
Update your charter and inform stakeholders | 2
Estimated Meeting Hours for "Analyze" | 16
Improve
Use team brainstorming to generate solutions | 3
Select and Develop Solutions | 4
Plan for a pilot of the solutions, if needed | 4
Plan for Implementation | 3
Implement solutions to address root causes | 2
Estimated Meeting Hours for "Improve" | 16
Control
Create a system and/or process to monitor the results | 4
Complete Documentation of processes & procedures | 4
Create Response Plans performance | 2
Hand over formal ownership to the process owner | 1
Estimated Meeting Hours for "Control" | 13