## Dashboard
Yellow Belt Tollgate Checklist
Details entered in top section will appear automatically on all Tollgate Checklist pages:
Yellow Belt: | Enter Yellow Belt | Project Start Date: | Enter Date
Project Name: | Enter Project Name | Planned Completion Date: | Enter Date
Champion: | Enter Champion/Sponsor
Done (Y/N) | Phase
N | Introduction
N | Define
N | Measure
N | Analyze
N | Improve
N | Control
Once all items above are marked "Y", item below will automatically marked "Y".
N | All Tollgates Complete

## Yellow Belt Intro Tollgate
Yellow Belt Introduction Tollgate Checklist
Yelllow Belt: | Enter Yellow Belt | Project Start Date: | Enter Date
Project Name: | Enter Project Name | Planned Completion Date: | Enter Date
Champion: | Enter Champion/Sponsor
Done (Y/N) | Introduction |  |  | Typical Duration (Hours)
N | Conduct an 8 Wastes Assessment |  |  | 0.5
N | Find at least one process improvement opportunity |  |  | 0.5
N | Enlist a Project Champion/Sponsor who will support you and the project |  |  | 0.5
N | Familiarize yourself with the DMAIC Roadmap |  |  | 0.5
Once all items above are marked "Y", item below will automatically marked "Y" and Dashboard will be updated. |  |  |  | 2
N | Introduction Tollgate Complete

## Yellow Belt Define Tollgate
Yellow Belt Define Tollgate Checklist
YEllow Belt: | Enter Yellow Belt | Project Start Date: | Enter Date
Project Name: | Enter Project Name | Planned Completion Date: | Enter Date
Champion: | Enter Champion/Sponsor
Done (Y/N) | Define |  |  | Typical Duration (Hours)
N | Complete the elements of the Project Charter |  |  | 1
N | Collect the Voice of the Customer and make customer requirements measurable |  |  | 0.5
N | Create a high-level and detailed map of the current state |  |  | 1
N | Update Charter and inform Stakeholders |  |  | 0.5
Once all items above are marked "Y", item below will automatically marked "Y" and Dashboard will be updated. |  |  |  | 3
N | Define Tollgate Complete

## Yellow Belt Measure Tollgate
Yellow Belt Measure Tollgate Checklist
Yellow Belt: | Enter Yellow Belt | Project Start Date: | Enter Date
Project Name: | Enter Project Name | Planned Completion Date: | Enter Date
Champion: | Enter Champion/Sponsor
Done (Y/N) | Measure |  |  | Typical Duration (Hours)
N | Select baseline measurements |  |  | 0.5
N | Develop a Data Collection Plan with Operational Definitions and create Check Sheets as needed |  |  | 1
N | Collect the Baseline Data |  |  | 1
N | Update Charter and inform Stakeholders |  |  | 0.5
Once all items above are marked "Y", item below will automatically marked "Y" and Dashboard will be updated. |  |  |  | 3
N | Measure Tollgate Complete

## Yellow Belt Analyze Tollgate
Yellow Belt Analyze Tollgate Checklist
Yellow Belt: | Enter Yellow Belt | Project Start Date: | Enter Date
Project Name: | Enter Project Name | Planned Completion Date: | Enter Date
Champion: | Enter Champion/Sponsor
Done (Y/N) | Analyze |  |  | Typical Duration (Hours)
N | Identify root causes using Process Analysis, 5 Whys or Fishbone Diagrams |  |  | 1
N | Develop root cause hypothesis |  |  | 1
N | Collect data to prove or disprove root cause hypotheses |  |  | 1
N | Update your Charter and inform Stakeholders |  |  | 1
Once all items above are marked "Y", item below will automatically marked "Y" and Dashboard will be updated. |  |  |  | 4
N | Analyze Tollgate Complete

## Yellow Belt Improve Tollgate
Yelllow Belt Improve Tollgate Checklist
Yellow Belt: | Enter Yellow Belt | Project Start Date: | Enter Date
Project Name: | Enter Project Name | Planned Completion Date: | Enter Date
Champion: | Enter Champion/Sponsor
Done (Y/N) | Improve |  |  | Typical Duration (Hours)
N | Use team brainstorming to generate solutions that address the root cause |  |  | 1
N | Run a Pilot of solutions if needed |  |  | 1
N | Implement solutions to address root causes |  |  | 1
N | Celebrate with the team and recognize them for their efforts |  |  | 1
Once all items above are marked "Y", item below will automatically marked "Y" and Dashboard will be updated. |  |  |  | 4
N | Improve Tollgate Complete

## Yellow Belt Control Tollgate
Yellow Belt Control Tollgate Checklist
Yellow Belt: | Enter Yellow Belt | Project Start Date: | Enter Date
Project Name: | Enter Project Name | Planned Completion Date: | Enter Date
Champion: | Enter Champion/Sponsor
Done (Y/N) | Control |  |  | Typical Duration (Hours)
N | Create a system and/or process to monitor the results |  |  | 1
N | Complete documentation of the processes and procedures |  |  | 1
N | Create Response Plans in case there is a drop in performance |  |  | 1
N | Hand over formal ownership to the Process Owner |  |  | 1
Once all items above are marked "Y", item below will automatically marked "Y" and Dashboard will be updated. |  |  |  | 4
N | Control Tollgate Complete

## (Original) Est. Meeting Times (hidden)
Define | Typical Duration (Hours)
Complete the elements of the Project Charter | 1
Collect the Voice of the Customer and make customer requirements measurable | 0.5
Create a high level and detailed map of the current state | 1
Create Stakeholder Communication Plan | 0.5
Update charter and project documentation | #REF!
Estimated Meeting Hours for "Define" | 3
Measure
Select baseline measures | 0.5
Develop a data collection plan with Operational Definitions and create data sheets if needed | 1
Collect the baseline data | 1
Update charter and inform stakeholders | 0.5
Estimated Meeting Hours for "Measure" | 3
Analyze
Identify potential causes (Process Maps, 5 Why’s, Fishbone) | 1
Develop root cause hypothesis | 1
Collect facts or data to support root cause hypothesis | 1
Update your charter and inform stakeholders | 1
Estimated Meeting Hours for "Analyze" | 4
Improve
Use team brainstorming to generate solutions | 1
Select and Develop Solutions | #REF!
Plan for a pilot of the solutions, if needed | 1
Plan for Implementation | 1
Implement solutions to address root causes | 1
Estimated Meeting Hours for "Improve" | 4
Control
Create a system and/or process to monitor the results | 1
Complete Documentation of processes & procedures | 1
Create Response Plans performance | 1
Hand over formal ownership to the process owner | #REF!
Estimated Meeting Hours for "Control" | 4